## Sheet1
Milestone(s) | Start Week | End Week | Description | Duration (Weeks)
Milestone 1 | 2018-09-10 | 2018-09-16 | Understanding What my Project is, what is required of me and how I can start | 2
| 2018-09-17 | 2018-09-30 | Research on the Python Programming Language and Various Libraries | 2
| 2018-10-01 | 2018-10-07 | Research on Alan Turing and the Turing Machine | 3
| 2018-10-08 | 2018-11-23 | Report on the Python Language, Alan Turing and my Evaluation | 4
Milestone 2 | 2018-11-26 | 2018-12-09 | UI Design for the Programmable Turing Machine | 2
| 2018-12-10 | 2018-12-30 | Initial Prototype for the Basic Implementation of my Turing Machine | 3
| 2018-12-31 | 2019-01-06 | Testing my First Prototype for any Errors in the Code | 1
| 2019-01-07 | 2019-01-20 | Implementing Extra Features to my Initial Prototype | 2
| 2019-01-21 | 2019-01-27 | Testing the Additional Features for Errors in the Code | 1
| 2019-01-28 | 2019-02-01 | Report on my Evaluation of the Second Milestone | 1
Milestone 3 | 2019-02-04 | 2019-02-17 | Design any Additional Features | 2
| 2019-02-18 | 2019-03-10 | Implement Any Additional Features to my Turing Machine | 3
| 2019-03-11 | 2019-03-17 | Test Additional Features | 1
| 2019-03-18 | 2019-03-29 | Report on how my Objectives have/have not been met | 2
Milestone 4 | 2019-04-01 | 2019-04-07 | Preparation for what my Presentation will cover | 1
| 2019-04-08 | 2019-04-14 | Creating the Presentation | 1
| 2019-04-15 | 2019-04-21 | Prepare a Demo of My Project | 1
| 2019-04-22 | 2019-05-03 | Creating a Poster for my Presentation | 1