## Slide 1
Milestone 4
Milestone 3
2018
2019
Today
Sep
Oct
Nov
Dec
2019
Feb
Mar
Apr
May
5 days
Understanding What my Project is, what is required of me and how I can start
Sep 10 - Sep 16
10 days
Research on the Python Programming Language and Various Libraries
Sep 17 - Sep 30
5 days
Research on Alan Turing and the Turing Machine
Oct 1 - Oct 7
35 days
Report on the Python Language, Alan Turing and my Evaluation
Oct 8 - Nov 23
10 days
UI Design for the Programmable Turing Machine
Nov 26 - Dec 9
15 days
Initial Prototype for the Basic Implementation of my Turing Machine
Dec 10 - Dec 30
5 days
Testing my First Prototype for any Errors in the Code
Dec 31 - Jan 6
10 days
Implementing Extra Features to my Initial Prototype
Jan 7 - Jan 20
5 days
Testing the Additional Features for Errors in the Code
Jan 21 - Jan 27
5 days
Report on my Evaluation of the Second Milestone
Jan 28 - Feb 1
10 days
Design any Additional Features
Feb 4 - Feb 17
15 days
Implement Any Additional Features to my Turing Machine
Feb 18 - Mar 10
5 days
Test Additional Features
Mar 11 - Mar 17
10 days
Report on how my Objectives have/have not been met
Mar 18 - Mar 29
5 days
Preparation for what my Presentation will cover
Apr 1 - Apr 7
5 days
Creating the Presentation
Apr 8 - Apr 14
5 days
Prepare a Demo of My Project
Apr 15 - Apr 21
10 days
Creating a Poster for my Presentation
Apr 22 - May 3
Milestone 2
Milestone 1